## Sheet1
| 1/1/2026 (Milestone 1) | (milestone 2) | (Milestone 3) | Milestone 4
Orchestrator
Progress Display
Show spinner for "in progress" | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Conversational real-time updates | ❌ No | ❌ No | ✅ Yes | ✅ Yes | Conversational real-time: "I've extracted 47 employees from your Payroll Register." then "Now validating..." then "Found a discrepancy - let me ask about that." (Delightful - feels like conversation, not status updates)
Document Management
Upload documents at start | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
AI uses all uploaded documents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Can remove documents | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Can ignore specific documents | ❌ No | ❌ No | ❌ No | ❌ No
AI selects best sources | ❌ No | ❌ No | ❌ No | ✅ Yes
AI explains document choices | ❌ No | ❌ No | ❌ No | ✅ Yes
User has control over sources | ❌ No (AI decides) | ❌ No (AI decides) | ✅ Yes (can remove) | ✅ Yes (with AI guidance)
State Management
Track completed agents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Know current agent position | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Resume from last completed | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Allow editing completed agents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Track dependencies between agents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Flag potentially affected agents when editing | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
AI detects inconsistencies across agents | ❌ No | ❌ No | ✅ Yes (proactive) | ✅ Yes (proactive)
Cross-agent validation | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Proactive warnings before approval | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Predict impact of changes | ❌ No | ❌ No | ❌ No | ✅ Yes
Show exactly which agents affected | ❌ No | ❌ No | ❌ No | ✅ Yes
Offer to auto-update dependent agents | ❌ No | ❌ No | ❌ No | ✅ Yes (with confirmation)
Skip Logic
Allow skip if not blocker | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Simple dependency rules enforced | ✅ Yes (Pay Period before Tax) | ✅ Yes | ✅ Yes | ✅ Yes
Show error if blocker skipped | ✅ Yes ("Complete [Agent X] first") | ✅ Yes | ✅ Yes | ✅ Yes
Track which agents were skipped | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Add skipped agents to to-do list | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Show reminder of skipped agents | ❌ No | ✅ Yes ("You have 3 skipped agents") | ✅ Yes | ✅ Yes
Explain why agent is blocked | ❌ No | ❌ No | ✅ Yes (if applicable) | ✅ Yes
Explain impact of skipping | ❌ No | ❌ No | ✅ Yes ("Skipping Retirement means no 401k setup") | ✅ Yes (detailed)
Smart suggestions for when to complete | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Document Processing Failure | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Show clear error message | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Ask user to re-upload | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Offer manual data entry | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Show specific error (quality, format) | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Offer retry option | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Auto-retry with different method | ❌ No | ❌ No | ❌ No | ✅ Yes
AI suggests specific fixes | ❌ No | ❌ No | ❌ No | ✅ Yes
Manual entry as fallback | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Session Resume
Resume from last completed agent | ✅ Yes (single user) | ✅ Yes (single user) | ✅ Yes (multi users) | ✅ Yes (multi users)
Save progress automatically | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Support multiple users | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Show progress when resuming | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Graceful messaging on resume | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Agent - data handling
Extraction
Extract from uploaded documents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Multiple document upload support | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Request specific documents if missing | ❌ No | ✅ Yes (per agent) | ✅ Yes | ✅ Yes
Conflict Detection
Detect conflicts within agent | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Detect from all uploaded documents and domains | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Provide context for the conflict | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Present side-by-side comparison | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Explain why conflict matters | ❌ No | ❌ No | ✅ Yes (if necessary) | ✅ Yes
User picks resolution | ❌ No | ✅ Yes (no explanation) | ✅ Yes | ✅ Yes
Distinguish system-constrained vs open-ended | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
AI suggests resolution | ❌ No | ❌ No | ❌ No | ✅ Yes (when can infer)
Explain reasoning behind suggestion | ❌ No | ❌ No | ❌ No | ✅ Yes
User can accept or override AI suggestion | ❌ No | ❌ No | ❌ No | ✅ Yes
Missing Information Requests
Ask directly for missing info | ✅ Yes ("What's your Federal EIN?") | ✅ Yes ("What's your Federal EIN?") | ✅ Yes | ✅ Yes
Provide context for why info needed | ❌ No | ✅ Yes ("This is your 9-digit IRS number") | ✅ Yes ("We need your EIN before configuring taxes") | ✅ Yes ("Your EIN enables tax filing...")
Block progression until provided | ❌ No | ✅ Yes (Acceptable - minimal friction) | ✅ Yes | ✅ Yes
Flag data with dependency context | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Flag required data with business impact | ❌ No | ❌ No | ❌ No | ✅ Yes
AI suggests resolution if appropriate | ❌ No | ❌ No | ❌ No | ✅ Yes
Summary format
Scannable and organized | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Agent specifies format based on guidelines | ❌ No | ✅ Yes (Acceptable - consistent) | ✅ Yes (Acceptable - consistent) | ❌ No
Centralized UI Decision Agent applies rules | ❌ No | ❌ No | ❌ No | ✅ Yes (Acceptable - consistent)
Adaptive to user needs | ❌ No | ❌ No | ❌ No | ✅ Yes (Delightful - intelligent, personalized)
User approves or requests changes | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Conversation Design
Clarity - Use plain words so a non-expert can answer on the first read.
Use simple, direct language | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Avoid technical and UKG jargon | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
One question at a time. | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Add context and define terms on first use | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Provide examples and visual aids | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Adapt clarity to user expertise | ❌ No | ❌ No | ❌ No | ✅ Yes
Brevity - Say the minimum needed for the user to act confidently.
No unncessary details | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Get to the point | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Suggested read more topics links | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Progressive disclosure | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Automatically adjusts how much it says (and how much it shows) depending on how experienced the user | ❌ No | ❌ No | ❌ No | ✅ Yes
Context awareness - Remember what was said earlier and use that information.
Don't re-ask info within agent, store answers | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Use context to pre-fill subsequent questions across agent | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Don't re-ask across agents (session-wide memory) | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Reference previous answers explicitly | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Detect contradictions in user input across agents | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Use context to predict needs | ❌ No | ❌ No | ❌ No | ✅ Yes
Track support package hours remaining | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Display support hours when relevant | ❌ No | ❌ No | ✅ Yes (when user asks or escalates) | ✅ Yes (proactively at decision points)
Proactively suggest support usage based on complexity | ❌ No | ❌ No | ❌ No | ✅ Yes (intelligent recommendations)
Consistency - Use the same patterns, words, and UI every time.
Same language patterns, buttons, checkpoint format | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Consistent conversation flow pattern - Questions → Review → Approve | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Consistent errors, confirmations, style guide | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Consistent examples, progress indicators | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Consistent adaptive behavior | ❌ No | ❌ No | ❌ No | ✅ Yes
Empathy & Tone - how warm, supportive, and human the AI feels.
Just functional. Baseline - don't confuse users. | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Functional, clear, slightly warmer | ❌ No | ✅ Yes | ❌ No | ❌ No
Friendly, reassuring, encouraging, celebrate progress | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Supportive, adaptive, personalized | ❌ No | ❌ No | ❌ No | ✅ Yes
Turn-Taking & Flow - How well the conversation flows back and forth.
Questions grouped by topic | questions grouped by topic, asked one at a time | Use question card UI to group topic | Use question card UI to group topic | ✅ Yes
Smooth transitions between question groups with context | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Detect user confusion/struggle, offer help | ❌ No | ❌ No | ✅ Yes (reactive - when user explicitly shows confusion) | ✅ Yes (proactive - detect subtle signals)
Rephrase when needed | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Interruption handling | ❌ No | ❌ No | ✅ Yes Basic (respond to explicit requests) | ✅ Graceful (context-aware, smooth recovery) | Phase 2: AI: "What's your pay period?" User: "Wait, go back to the employee count question" AI: "Okay, going back. How many employees do you have?" | Phase 3: AI: "What's your pay period?" User: "Actually, I'm not sure about those employee numbers I gave you earlier" AI: "No problem! Let's revisit that. You mentioned 47 employees - what would you like to adjust? Once we've updated that, we'll come right back to setting up your pay period."
Detect user state (confused/frustrated/impatient) | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Adapt pacing and approach dynamically. Adjusts its communication style and speed in real-time based on how the user is responding | ❌ No | ❌ No | ❌ No | ✅ Yes | What is this? For example, if a user seems confident and answers quickly, the AI moves faster with less explanation, but if someone hesitates or asks for help, it slows down and provides more examples and reassurance.
Proactive clarification | ❌ No | ❌ No | ❌ No | ✅ Yes
Handle tangential questions | ❌ No | ❌ No | ✅ Yes | ✅ Yes | Phase 2 AI can answer tangential questions but then returns to flow: "Great question about overtime rules. Now back to your pay period..." | Phase 3 Yes (Advanced) - AI intelligently determines if tangential question is relevant to current setup, may adjust flow accordingly
Graceful exit/pause handling (User says "I need to stop and come back") | ✅ Yes- AI acknowledges pause: "No problem! I've saved your progress. You can pick up right here when you're ready. | Same as Phase 0.5 | ✅ Yes (Advanced) - AI proactively suggests breaks for long sessions: "This is a good stopping point. Want to continue or come back later?" | Same as phase 2
Multi-Turn Management
Allow clarifying questions ("What does this mean?") | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Provide examples when requested | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Return to original question after clarification | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Turn limit with escalation prompt | ✅ Yes (5 turns → "contact PM, create Jira???") | ✅ Yes (5 turns → "contact PM, create Jira???") | ✅ Yes (8-10 turns → "Contact your support team" or "Schedule support session") | ✅ Yes (flexible limit → Smart escalation based on complexity + support package hours)
Handle user corrections mid-conversation | ❌ No | ❌ No | ✅ Yes | ✅ Yes
AI proactively offers help/clarification | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Rephrase questions multiple ways | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Track full conversation thread/context | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Reference earlier turns in conversation | ❌ No | ❌ No | ❌ No | ✅ Yes
Intelligently determine when to move forward | ❌ No | ❌ No | ❌ No | ✅ Yes
Adapt conversation depth based on user confidence | ❌ No | ❌ No | ❌ No | ✅ Yes
CONFIRMATION & FEEDBACK - Acknowledging user input and showing what will happen next.
Acknowledge input, show checkpoint, confirm completion | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Repeat back complex inputs for verification | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Show progress, celebrate milestones, show impact | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Predictive feedback, explain consequences, simulations | ❌ No | ❌ No | ❌ No | ✅ Yes
Proactive Guidance - AI anticipates what user needs and offers help before being asked.
User must ask for help (reactive only) | ✅ Yes (AI waits for questions) | ❌ No | ❌ No | ❌ No
Static help text | ❌ No | ✅ Yes ("Need help? Click here") | ✅ Yes | ✅ Yes
Detect when user might need help | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Anticipate needs, proactive warnings, smart suggestions, tips | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Suggest next steps | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Proactive warnings about consequences | ❌ No | ❌ No | ❌ No | ✅ Yes
Smart suggestions based on context | ❌ No | ❌ No | ❌ No | ✅ Yes
Contextual tips based on company size/type | ❌ No | ❌ No | ❌ No | ✅ Yes
Suggest scheduling support at optimal times | ❌ No | ❌ No | ❌ No | ✅ Yes (calendar awareness, section complexity)
Error Handling
Document upload failure | ✅ Retry upload, Manual entry, Contact Support (Slack) | ✅ Same | ✅ Same + tracking | ✅ Same
Document extraction failure | ✅ Show generic error, Retry or Manual entry, Contact PM | ✅ Show specific error (quality/format), Retry or Manual entry, Contact Support | ✅ Same + auto-retry once | ✅ AI suggests specific fix (e.g., "Try CSV export from QuickBooks")
Validation errors (invalid user input) | ✅ Show inline error, Explain correct format, User re-enters | ✅ Same + validation examples | ✅ Real-time validation | ✅ Predictive validation, AI auto-corrects simple errors
Configuration failure (system can't configure) | ✅ Log error, Show "Contact PM" (Slack??), Continue to next agent | ✅ Show specific error, Retry or Skip to to-do list | ✅ Same | ✅ Auto-retry once, Smart escalation to specialist
AI processing errors (LLM timeout, invalid response) | ✅ Show generic error, Retry conversation, Contact PM | ✅ Same | ✅ Same | ✅ Smart recovery, fallback to simpler prompts
Network/system errors | ✅ Show generic error, Retry, Contact PM | ✅ Same | ✅ Same | ✅ Graceful degradation, queue for later
Monitoring AI for unexpected behaviors during use
Manual review of test sessions | ✅ Internal team reviews 100% of test sessions, Flag unexpected behaviors in Slack (No automated tracking - rely on hands-on observation) | ✅ Review 50% of sessions (rest covered by automated logging) | ✅ Review 20% of sessions (rest covered by automated analysis) | ✅ Review 10% of sessions (mostly automated monitoring)
Logging AI decisions and behaviors | ❌ No automated logging | ✅ Log all AI decisions (which document used, routing choices, assumptions made), Track metrics: frequency of AI assumptions, validation skip rate, confidence score distribution | ✅ Same + Automated behavioral analysis (Detect patterns, Compare AI behavior across user types, Monthly reports on emergent patterns) | ✅ Same + Real-time behavioral monitoring with automatic intervention
Automated alerts and intervention | ❌ No automated alerts - rely on manual observation only | ✅ Automated alerts for obvious issues (AI errors out repeatedly, AI skips required validation steps, Unusually high/low confidence scores) | ✅ Same + Proactive pattern detection (AI asking same question repeatedly, AI developing consistent shortcuts, User feedback: "Did AI do anything unexpected?") | ✅ Same + Automatic intervention (Flag problematic patterns for immediate review, Test and integrate beneficial shortcuts, Continuous learning feedback loop)
SOURCE ATTRIBUTION (CONVERSATIONAL)
Report which documents | ✅ Specific | ✅ Specific | ✅ Specific | ✅ Specific
Document name mentioned | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
User can view original | ❌ No | ❌ No | ✅ Click to view | ✅ Click to view
Link external sources | ❌ No | ❌ No | ❌ No | ✅ Yes
Correction Handling
Accept user corrections | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Use corrected values within agents | ✅ Yes | ✅ Yes | ✅ Consistently | ✅ Consistently
Log corrections | ❌ No | ✅ Internal | ✅ Internal | ✅ Internal
Track patterns | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Don't repeat mistakes | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Escalate after 3 corrections | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Adapt approach | ❌ No | ❌ No | ❌ No | ✅ Yes
Error Messages
User-friendly language | ✅ Generic | ✅ Generic | ✅ Specific | ✅ Context-aware
Not technical | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Explain what went wrong | ✅ Basic | ✅ Basic | ✅ Better | ✅ Detailed
Provide next steps | ❌ No | ❌ No | ✅ Yes | ✅ Personalized
Show specific error details | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Suggest vendor-specific fixes | ❌ No | ❌ No | ❌ No | ✅ Yes
Context-aware suggestions | ❌ No | ❌ No | ❌ No | ✅ Yes
Performance Targets
Time per agent - Target time | 6-10 min | 5-8 min | 3-5 min | 2-3 min
Time per agent - Within target | ⚠️ 50% | ✅ 60% | ✅ 75% | ✅ 85%
Total time - Target time | 90-150 min | 75-120 min | 45-75 min | 30-45 min
Total time - Within target | ⚠️ 50% | ✅ 60% | ✅ 75% | ✅ 85%
Agent Response time per turn | 7-10s | 7-10s | 4-7s | 0-3s
Within target | ✅75% | ✅90% | ✅ 95% | ✅99%
Extraction coverage - Fields found | 80%+ | 85%+ | 95%+ | 99%+
Extraction accuracy - Correctness | 80%+ | 85%+ | 92%+ | 95%+
Completion rate - All 15 agents | 100% | 100% | 100% | 100%
Completion rate - Meets target | ✅ Excellent | ✅ Excellent | ✅ Excellent | ✅ Excellent
Support escalations - Need help | <40% | <30% | <15% | <5%
Support escalations - Meets target | ⚠️ Acceptable | ✅ Functional | ✅ Good | ✅ Excellent

## out dated
Note: This list focuses on user and conversation experience success criteria. It represents a subset of the overall criteria, with additional criteria determined by the product and engineering teams.
Phase | Timeline | Audience | UX Goal
Phase 0.5 | 2025-01-15 | Internal team | Function
Phase 1 | TBD | Internal team | Basic acceptable - "Does it work?" |  | Conversation design = clear questions + basic error messages (not empathy or brand voice) Success = team completes setup and can identify bugs vs. design limitations
Phase 2 | TBD | Beta customers | Good - "Is it pleasant?"
Phase 3 | TBD | All customers | Delightful - "Do users love it?"
M1 deliverable
Capability | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Ochestrator responsibilities
Progress Display | In progress - spinner | In progress - spinner | Detailed per-agent: (1) Extracted employee data (complete), (2) Validated information (complete), (3) Checking for conflicts (in progress - spinner), (4) Preparing summary. (Good - user knows what's happening) | Conversational real-time: "I've extracted 47 employees from your Payroll Register." then "Now validating..." then "Found a discrepancy - let me ask about that." (Delightful - feels like conversation, not status updates)
Document Management | Upload at start. AI uses all documents. Can't remove or ignore documents. (Acceptable - basic functionality) | Upload at start. AI uses all documents. Can't remove or ignore documents. (Acceptable - basic functionality) | Upload at start. Can remove documents, AI re-extracts. (Good - user has control) | same as phase 2
State Management (The data layer (what happened) | •Track completed agents •Know current agent position •Resume from last completed agent Allow editing completed agents (via conversation) •DOES NOT FLAG potentially affected agents when editing | •Phase 0.5 plus •Track dependencies between agents •Flag potentially affected agents when editing | •Everything from Phase 1, PLUS: •AI detects inconsistencies across agents during flow •Cross-agent validation •Proactive warnings before approval [Example: "You said bi-weekly earlier but this shows semi-monthly. Which is correct?"] | •Everything from Phase 2, PLUS: •Predict impact before user commits changes •Show exactly which agents will be affected Offer to auto-update dependent agents (with confirmation) Example: "Changing to bi-weekly will affect 3 areas. Should I update those automatically?" | What it does: Stores and tracks data • Tracks which agents are complete/in-progress/blocked • Stores user's answers • Remembers what's been configured • Keeps the current position What it DOESN'T do: Decide what happens next
Skip Logic [Business rules (what's allowed)] | •Allow skip if agent is NOT a blocker for others •Simple dependency rules: Pay Period before Tax Codes, etc. •If blocked, show error: "Complete [Agent X] first" | •Everything from Phase 0.5, PLUS: •Track which agents were skipped •Add skipped agents to a to-do list •Show reminder: "You have 3 skipped agents" | •Everything from Phase 1, PLUS: •Explain why agent is blocked (if applicable) •Explain impact of skipping: "Skipping Retirement means no 401k setup" | Priority flagging (mark some skipped agents as "recommended to complete before launch") | What it does: Decides if user can skip an agent Uses State Management to check: Is this agent a blocker for others? Has user provided required info? Are there dependencies? Then decides: Allow skip OR Block skip Without Skip Logic: State Management just tracks status System doesn't know WHEN skipping is allowed No rules for what can/can't be skipped
Session Resume | Resume from last completed agent (one single user) | Resume from last completed agent (one single user) | Resume from last completed agent, multi users | Resume from last completed agent, multi users | What it does: Uses State Management to bring user back to the right place How it works: •User leaves mid-setup •State Management saved: "Completed agents 1-5, in progress on agent 6" •User returns •Session Resume reads State Management and says: "Resume from agent 6" Without Session Resume: •State Management stores the data •But system doesn't know HOW to use it to resume •Need logic to: Load saved state → Restore UI → Position user correctly
Agent responsibilities - data handling
Extraction | Extraction threshold: Extract 80% of the information needed for configuration requirements from the document. Accuracy threshold: 80% accurate from this information | Mulitple documents upload, plus the ability to request specific documents per agent if missing | Same as phase 1 | Same as phase 1
Inconsistency Clarification | OUT OF SCOPE | Provide context for the conflict Present side-by-side comparison Distinguish between system-constrained vs. open-ended conflicts User picks one No explanation of "why it matters" | Detect from uploaded documents and all domains, explain why it matters (if necessary) | AI suggests resolution when it can infer the answer Explains reasoning behind suggestion User can accept or override
Missing Information Requests | Ask Clarifying Questions | Ask directly: "What's your Federal EIN? This is your 9-digit number from the IRS." Block progression until provided. (Acceptable - minimal friction) | Flag data with dependency context: "We need your EIN before configuring payroll taxes. This is your 9-digit IRS number. | Flag required data with business impact: "Your EIN enables tax filing, state registration, and W-2 generation. AI suggests resolution (if appropriate)
Summary | Scannable and organized Agent specifies format based on guidelines. (Acceptable - consistent, organized) | Scannable and organized Agent specifies format based on guidelines. (Acceptable - consistent, organized) | Centralized UI Decision Agent applies basic rules using agent metadata: If data.rows >3 → table, else → list. Consistent formatting across agents. User approves or requests changes. (Good - consistent, predictable | Advanced UI Decision Agent analyzes data complexity, user context, and optimal cognitive load. Adaptive to user needs. (Delightful - intelligent, personalized)
Output Format | Agents return data and specify their own UI component. | Agents return data and specify their own UI component | Agents return data with metadata. Basic centralized UI Decision Agent. | Intelligent format selection based on: Data complexity: Simple vs. nested vs. hierarchical Data volume: 5 items vs. 50 items vs. 500 items User context: First-time user vs. expert, mobile vs. desktop Cognitive load: How much has user reviewed already? Are they fatigued? Data relationships: Are there parent-child relationships? Dependencies?
Agent responsibilities - conversation
Tone | Dependent on Framework. | Functional, clear (baseline - don't confuse users) | Clear, friendly, reassuring, encouraging (pleasant - reduce anxiety, celebrate progress) | Clear, friendly, reassuring, encouraging, supportive, adaptive to user skill level (delightful - anticipate needs, personalize)
Conversation Flow Basics | Agent asks question → waits for answer → moves to next question. Basic clarification if input invalid. Agent stays in its domain. (Acceptable - straightforward Q&A) | Agent asks question → waits for answer → moves to next question. Basic clarification if input invalid. Agent stays in its domain. (Acceptable - straightforward Q&A) | Agent detects confusion, rephrases questions. Offers contextual help. Handles tangents gracefully. (Good - flexible conversatio | Agent adapts questioning style to user. Predicts follow-up questions. Natural multi-turn dialogue. (Delightful - feels like conversation with expert)
e | Meet 2.5 | Clarify conflicts -->
Question Design | Dependent on Framework. | Direct, single-purpose: "What's your EIN?" (Acceptable - one thing at a time) | With context: "To file taxes, I need your EIN. This is the 9-digit IRS number. What's your EIN?" (Good - explains why) | With context + examples: "Your EIN appears on IRS paperwork as 12-3456789. Where can I find this?" (Delightful - educational)
Turn Management | Dependent on Framework. | Bot asks → user responds → bot acknowledges. Clarifies if unclear. User completes current question before proceeding. (Acceptable - basic Q&A) | User can provide info out of order. Bot asks follow-ups to fill gaps. Handles tangential questions gracefully. (Good - flexible conversation) | Bot detects interruptions and changes direction. Adapts to user's response style. Handles multiple topics in one message. (Delightful - natural dialogue)
Question Clarity | Dependent on Framework. | Direct questions (acceptable - functional) | Questions with context and examples (good - helpful and clear) | Questions with context, examples, and why it matters (delightful - educational)
Context Maintenance | Dependent on Framework. | Don't re-ask provided info | Reference previous answers ("Earlier you said 47 employees...") | Full conversation memory, Detect contradictions
Source Attribution (Conversational) | To be included in M2 | Report which documents used (acceptable - basic transparency) | Report which documents used, user can view original documents (good - verifiable) | Report which documents used, user can view original documents, link to external sources (e.g., federal websites) when cited (delightful - comprehensive transparency)
Emotional Intelligence | None | None. Bot doesn't detect user emotional state. Internal team will report issues directly(?) . (Acceptable - no emotional detection needed) | Bot detects obvious frustration signals ("this is confusing", multiple errors). Offers help: "I see you're having trouble. Would you like me to explain this differently or connect you with support?" (Good - reactive emotional support) | Bot proactively detects user state (confused/frustrated/impatient) from subtle cues. Adapts pacing and approach dynamically. Offers reassurance before user asks. Celebrates progress to reduce fatigue. (Delightful - emotionally adaptive)
Error handling
Error Messages | Agent takes this decision currently. Dependent on Agent FW - on classification for non-readable documents (Need to assess with Engineering) | Generic user-friendly: "I had trouble reading your document. Can you upload a clearer version?" (acceptable - not technical) | Specific user-friendly with next steps: "The Payroll Register scan is too blurry to read employee names. Upload a CSV export or higher quality scan." (good - actionable guidance) | Context-aware and personalized: "Based on your setup, I need clearer data for employee tax withholdings. Try exporting from [vendor] using [specific report name]." (delightful - tailored to user's situation)
Recovery Options | AI gives followin option: Retry action, Enter data manually (if extraction fails), Skip (if not blocker) | AI gives followin option: Retry action, Enter data manually (if extraction fails), Skip (if not blocker) | Same as Phase 1, plus AI suggests which recovery action to try | AI auto-retries with different method, Suggests specific fixes, Same self-service options available
Escalation | Internal users - Solved internally | Contact product team available?? | Contact product team available?? | AI proactively offers 40hr support package when detecting struggle
Metric
Time per Agent | 5-8 minutes | 5-8 minutes | 3-5 minutes | 2-3 minutes
Total Implementation Time |  | ? | ? | ?
Extraction Accuracy | * Needs Clarity | 85%+ per agent | 92%+ per agent | 95%+ per agent
User Satisfaction | "Functional - gets job done" | "Functional - gets job done" | "Good - pleasant experience" | "Excellent - feels intelligent"
Completion Rate | * All steps are completed by agent * Consultant can still edit if anything was missing. | 70%+ complete all payroll agents | 85%+ complete all payroll agents | 95%+ complete all payroll agents
Support Escalations | N/A | <30% of implementations need help | <15% need help | <5% need help
Agent response time | Dependent on Agent Framework | 7-10s | 4-7s | 3s and less
Emergent Behaviors | * Needs Clarity | Tack identifu whethear is a feature or bug | display affordances" report issue, identify issue" ask AI show reasoning
Use simple, direct language. Avoid technical jargon. One question at a time. Clear instructions: "Enter your pay period" (Acceptable - functional)Everything from Phase 0.5, PLUS: Add brief context when needed. Define terms on first use: "Pay period (how often you pay employees)" (Functional - basic clarity)Everything from Phase 1, PLUS: Provide examples with questions. Use "See an example" links for complex concepts. Visual aids where helpful (Good - helpful and clear)Everything from Phase 2, PLUS: Adapt clarity level to user expertise. Proactively clarify before complex questions: "Let me explain why I'm asking this..." (Delightful - educational)
| 80% | extraction
| 80% | accuracy

## checklist
Capability | Phase 0.5 (Jan) | Phase 1 (Feb) | Phase 2 (Mar) | Phase 3 (Jun)
Conversation Design
Clarity - Use plain words so a non-expert can answer on the first read.
Use simple, direct language | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Avoid technical and UKG jargon | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
One question at a time. | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Add context and define terms on first use | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Provide examples and visual aids | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Adapt clarity to user expertise | ❌ No | ❌ No | ❌ No | ✅ Yes
Brevity - Say the minimum needed for the user to act confidently.
No unncessary details | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Get to the point | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Suggested read more topics links | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Progressive disclosure | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Automatically adjusts how much it says (and how much it shows) depending on how experienced the user | ❌ No | ❌ No | ❌ No | ✅ Yes
Context awareness - Remember what was said earlier and use that information.
Don't re-ask info within agent, store answers | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Use context to pre-fill subsequent questions across agent | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Don't re-ask across agents (session-wide memory) | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Reference previous answers explicitly | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Detect contradictions in user input across agents | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Use context to predict needs | ❌ No | ❌ No | ❌ No | ✅ Yes
Track support package hours remaining | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Display support hours when relevant | ❌ No | ❌ No | ✅ Yes (when user asks or escalates) | ✅ Yes (proactively at decision points)
Proactively suggest support usage based on complexity | ❌ No | ❌ No | ❌ No | ✅ Yes (intelligent recommendations)
Consistency - Use the same patterns, words, and UI every time.
Same language patterns, buttons, checkpoint format | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Consistent conversation flow pattern - Questions → Review → Approve | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Consistent errors, confirmations, style guide | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Consistent examples, progress indicators | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Consistent adaptive behavior | ❌ No | ❌ No | ❌ No | ✅ Yes
Empathy & Tone - how warm, supportive, and human the AI feels.
Just functional. Baseline - don't confuse users. | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Functional, clear, slightly warmer | ❌ No | ✅ Yes | ❌ No | ❌ No
Friendly, reassuring, encouraging, celebrate progress | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Supportive, adaptive, personalized | ❌ No | ❌ No | ❌ No | ✅ Yes
Turn-Taking & Flow - How well the conversation flows back and forth.
Questions grouped by topic | questions grouped by topic, asked one at a time | Use question card UI to group topic | Use question card UI to group topic | ✅ Yes
Smooth transitions between question groups with context | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Detect user confusion/struggle, offer help | ❌ No | ❌ No | ✅ Yes (reactive - when user explicitly shows confusion) | ✅ Yes (proactive - detect subtle signals)
Rephrase when needed | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Interruption handling | ❌ No | ❌ No | ✅ Yes Basic (respond to explicit requests) | ✅ Graceful (context-aware, smooth recovery) | Phase 2: AI: "What's your pay period?" User: "Wait, go back to the employee count question" AI: "Okay, going back. How many employees do you have?" | Phase 3: AI: "What's your pay period?" User: "Actually, I'm not sure about those employee numbers I gave you earlier" AI: "No problem! Let's revisit that. You mentioned 47 employees - what would you like to adjust? Once we've updated that, we'll come right back to setting up your pay period."
Detect user state (confused/frustrated/impatient) | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Adapt pacing and approach dynamically. Adjusts its communication style and speed in real-time based on how the user is responding | ❌ No | ❌ No | ❌ No | ✅ Yes | What is this? For example, if a user seems confident and answers quickly, the AI moves faster with less explanation, but if someone hesitates or asks for help, it slows down and provides more examples and reassurance.
Proactive clarification | ❌ No | ❌ No | ❌ No | ✅ Yes
Handle tangential questions | ❌ No | ❌ No | ✅ Yes | ✅ Yes | Phase 2 AI can answer tangential questions but then returns to flow: "Great question about overtime rules. Now back to your pay period..." | Phase 3 Yes (Advanced) - AI intelligently determines if tangential question is relevant to current setup, may adjust flow accordingly
Graceful exit/pause handling (User says "I need to stop and come back") | ✅ Yes- AI acknowledges pause: "No problem! I've saved your progress. You can pick up right here when you're ready. | Same as Phase 0.5 | ✅ Yes (Advanced) - AI proactively suggests breaks for long sessions: "This is a good stopping point. Want to continue or come back later?" | Same as phase 2
Multi-Turn Management
Allow clarifying questions ("What does this mean?") | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Provide examples when requested | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Return to original question after clarification | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Turn limit with escalation prompt | ✅ Yes (5 turns → "contact PM, create Jira???") | ✅ Yes (5 turns → "contact PM, create Jira???") | ✅ Yes (8-10 turns → "Contact your support team" or "Schedule support session") | ✅ Yes (flexible limit → Smart escalation based on complexity + support package hours)
Handle user corrections mid-conversation | ❌ No | ❌ No | ✅ Yes | ✅ Yes
AI proactively offers help/clarification | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Rephrase questions multiple ways | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Track full conversation thread/context | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Reference earlier turns in conversation | ❌ No | ❌ No | ❌ No | ✅ Yes
Intelligently determine when to move forward | ❌ No | ❌ No | ❌ No | ✅ Yes
Adapt conversation depth based on user confidence | ❌ No | ❌ No | ❌ No | ✅ Yes
CONFIRMATION & FEEDBACK - Acknowledging user input and showing what will happen next.
Acknowledge input, show checkpoint, confirm completion | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Repeat back complex inputs for verification | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Show progress, celebrate milestones, show impact | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Predictive feedback, explain consequences, simulations | ❌ No | ❌ No | ❌ No | ✅ Yes
Proactive Guidance - AI anticipates what user needs and offers help before being asked.
User must ask for help (reactive only) | ✅ Yes (AI waits for questions) | ❌ No | ❌ No | ❌ No
Static help text | ❌ No | ✅ Yes ("Need help? Click here") | ✅ Yes | ✅ Yes
Detect when user might need help | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Anticipate needs, proactive warnings, smart suggestions, tips | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Suggest next steps | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Proactive warnings about consequences | ❌ No | ❌ No | ❌ No | ✅ Yes
Smart suggestions based on context | ❌ No | ❌ No | ❌ No | ✅ Yes
Contextual tips based on company size/type | ❌ No | ❌ No | ❌ No | ✅ Yes
Suggest scheduling support at optimal times | ❌ No | ❌ No | ❌ No | ✅ Yes (calendar awareness, section complexity)
Error Handling
Document upload failure | ✅ Retry upload, Manual entry, Contact Support (Slack) | ✅ Same | ✅ Same + tracking | ✅ Same
Document extraction failure | ✅ Show generic error, Retry or Manual entry, Contact PM | ✅ Show specific error (quality/format), Retry or Manual entry, Contact Support | ✅ Same + auto-retry once | ✅ AI suggests specific fix (e.g., "Try CSV export from QuickBooks")
Validation errors (invalid user input) | ✅ Show inline error, Explain correct format, User re-enters | ✅ Same + validation examples | ✅ Real-time validation | ✅ Predictive validation, AI auto-corrects simple errors
Configuration failure (system can't configure) | ✅ Log error, Show "Contact PM" (Slack??), Continue to next agent | ✅ Show specific error, Retry or Skip to to-do list | ✅ Same | ✅ Auto-retry once, Smart escalation to specialist
AI processing errors (LLM timeout, invalid response) | ✅ Show generic error, Retry conversation, Contact PM | ✅ Same | ✅ Same | ✅ Smart recovery, fallback to simpler prompts
Network/system errors | ✅ Show generic error, Retry, Contact PM | ✅ Same | ✅ Same | ✅ Graceful degradation, queue for later
Monitoring AI for unexpected behaviors during use
Manual review of test sessions | ✅ Internal team reviews 100% of test sessions, Flag unexpected behaviors in Slack (No automated tracking - rely on hands-on observation) | ✅ Review 50% of sessions (rest covered by automated logging) | ✅ Review 20% of sessions (rest covered by automated analysis) | ✅ Review 10% of sessions (mostly automated monitoring)
Logging AI decisions and behaviors | ❌ No automated logging | ✅ Log all AI decisions (which document used, routing choices, assumptions made), Track metrics: frequency of AI assumptions, validation skip rate, confidence score distribution | ✅ Same + Automated behavioral analysis (Detect patterns, Compare AI behavior across user types, Monthly reports on emergent patterns) | ✅ Same + Real-time behavioral monitoring with automatic intervention
Automated alerts and intervention | ❌ No automated alerts - rely on manual observation only | ✅ Automated alerts for obvious issues (AI errors out repeatedly, AI skips required validation steps, Unusually high/low confidence scores) | ✅ Same + Proactive pattern detection (AI asking same question repeatedly, AI developing consistent shortcuts, User feedback: "Did AI do anything unexpected?") | ✅ Same + Automatic intervention (Flag problematic patterns for immediate review, Test and integrate beneficial shortcuts, Continuous learning feedback loop)
SOURCE ATTRIBUTION (CONVERSATIONAL)
Report which documents | ✅ Specific | ✅ Specific | ✅ Specific | ✅ Specific
Document name mentioned | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
User can view original | ❌ No | ❌ No | ✅ Click to view | ✅ Click to view
Link external sources | ❌ No | ❌ No | ❌ No | ✅ Yes
Correction Handling
Accept user corrections | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Use corrected values within agents | ✅ Yes | ✅ Yes | ✅ Consistently | ✅ Consistently
Log corrections | ❌ No | ✅ Internal | ✅ Internal | ✅ Internal
Track patterns | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Don't repeat mistakes | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Escalate after 3 corrections | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Adapt approach | ❌ No | ❌ No | ❌ No | ✅ Yes
Error Messages
User-friendly language | ✅ Generic | ✅ Generic | ✅ Specific | ✅ Context-aware
Not technical | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Explain what went wrong | ✅ Basic | ✅ Basic | ✅ Better | ✅ Detailed
Provide next steps | ❌ No | ❌ No | ✅ Yes | ✅ Personalized
Show specific error details | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Suggest vendor-specific fixes | ❌ No | ❌ No | ❌ No | ✅ Yes
Context-aware suggestions | ❌ No | ❌ No | ❌ No | ✅ Yes
Performance Targets
Time per agent - Target time | 6-10 min | 5-8 min | 3-5 min | 2-3 min
Time per agent - Within target | ⚠️ 50% | ✅ 60% | ✅ 75% | ✅ 85%
Total time - Target time | 90-150 min | 75-120 min | 45-75 min | 30-45 min
Total time - Within target | ⚠️ 50% | ✅ 60% | ✅ 75% | ✅ 85%
Agent Response time per turn | 7-10s | 7-10s | 4-7s | 0-3s
Within target | ✅75% | ✅90% | ✅ 95% | ✅99%
Extraction coverage - Fields found | 80%+ | 85%+ | 95%+ | 99%+
Extraction accuracy - Correctness | 80%+ | 85%+ | 92%+ | 95%+
Completion rate - All 15 agents | 100% | 100% | 100% | 100%
Completion rate - Meets target | ✅ Excellent | ✅ Excellent | ✅ Excellent | ✅ Excellent
Support escalations - Need help | <40% | <30% | <15% | <5%
Support escalations - Meets target | ⚠️ Acceptable | ✅ Functional | ✅ Good | ✅ Excellent
Progress Display | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Show spinner for "in progress" | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Basic stage tracking (4 stages) | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Detailed per-agent stages | ❌ No | ❌ No | ✅ Yes (5 detailed stages) | ❌ No
Conversational real-time updates | ❌ No | ❌ No | ❌ No | ✅ Yes
Show what's being extracted | ❌ No | ❌ No | ✅ Yes ("Extracted employee data") | ✅ Yes (with counts)
Show what's being validated | ❌ No | ❌ No | ✅ Yes ("Validated information") | ✅ Yes (conversational)
Show conflict checking status | ❌ No | ❌ No | ✅ Yes ("Checking for conflicts") | ✅ Yes ("Found a discrepancy")
Feels like conversation vs status | ❌ No | ❌ No | ❌ No | ✅ Yes
```
---
### **2. Document Management**
```
Document Management | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Upload documents at start | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
AI uses all uploaded documents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Can remove documents | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Can ignore specific documents | ❌ No | ❌ No | ❌ No | ❌ No
AI re-extracts after removal | ❌ No | ❌ No | ✅ Yes | ✅ Yes
AI selects best sources | ❌ No | ❌ No | ❌ No | ✅ Yes
AI explains document choices | ❌ No | ❌ No | ❌ No | ✅ Yes
User has control over sources | ❌ No (AI decides) | ❌ No (AI decides) | ✅ Yes (can remove) | ✅ Yes (with AI guidance)
```
---
### **3. Overall Progress**
```
Overall Progress | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Show current agent only | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Show completed agents count | ❌ No | ❌ No | ❌ No | ❌ No
Show what's next | ❌ No | ❌ No | ✅ Yes ("Now: Employee Information") | ✅ Yes (with context)
Group agents meaningfully | ❌ No | ❌ No | ❌ No | ✅ Yes ("Payroll essentials done")
Reduce perceived effort | ❌ No | ❌ No | ❌ No | ✅ Yes (grouping reduces overwhelm)
Context about what's complete | ❌ No | ❌ No | ✅ Yes ("Tax setup complete") | ✅ Yes (detailed grouping)
```
---
### **4. State Management**
```
State Management | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Track completed agents | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Know current agent position | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Resume from last completed | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Allow editing completed agents | ✅ Yes (via conversation) | ✅ Yes (via conversation) | ✅ Yes (via conversation) | ✅ Yes (via conversation)
Track dependencies between agents | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Flag potentially affected agents when editing | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
AI detects inconsistencies across agents | ❌ No | ❌ No | ✅ Yes (proactive) | ✅ Yes (proactive)
Cross-agent validation | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Proactive warnings before approval | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Predict impact of changes | ❌ No | ❌ No | ❌ No | ✅ Yes
Show exactly which agents affected | ❌ No | ❌ No | ❌ No | ✅ Yes
Offer to auto-update dependent agents | ❌ No | ❌ No | ❌ No | ✅ Yes (with confirmation)
```
---
### **5. Skip Logic**
```
Skip Logic | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Allow skip if not blocker | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Simple dependency rules enforced | ✅ Yes (Pay Period before Tax) | ✅ Yes | ✅ Yes | ✅ Yes
Show error if blocker skipped | ✅ Yes ("Complete [Agent X] first") | ✅ Yes | ✅ Yes | ✅ Yes
Track which agents were skipped | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Add skipped agents to to-do list | ❌ No | ✅ Yes | ✅ Yes | ✅ Yes
Show reminder of skipped agents | ❌ No | ✅ Yes ("You have 3 skipped agents") | ✅ Yes | ✅ Yes
Explain why agent is blocked | ❌ No | ❌ No | ✅ Yes (if applicable) | ✅ Yes
Explain impact of skipping | ❌ No | ❌ No | ✅ Yes ("Skipping Retirement means no 401k setup") | ✅ Yes (detailed)
AI explains impact before skip | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Smart suggestions for when to complete | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Priority flagging for skipped agents | ❌ No | ❌ No | ❌ No | ✅ Yes ("recommended before launch")
```
---
### **6. Document Processing Failure**
```
Document Processing Failure | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Show clear error message | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Ask user to re-upload | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Offer manual data entry | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Show specific error (quality, format) | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Offer retry option | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Auto-retry with different method | ❌ No | ❌ No | ❌ No | ✅ Yes
AI suggests specific fixes | ❌ No | ❌ No | ❌ No | ✅ Yes
Manual entry as fallback | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
```
---
### **7. Validation Failure**
```
Validation Failure | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Show error inline | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Explain correct format | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Ask user to re-enter | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Show error with example | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Suggest correction | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Validate in real-time | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Predictive validation | ❌ No | ❌ No | ❌ No | ✅ Yes
AI auto-corrects simple errors | ❌ No | ❌ No | ❌ No | ✅ Yes
Ask confirmation for corrections | ❌ No | ❌ No | ❌ No | ✅ Yes
```
---
### **8. Configuration Failure**
```
Configuration Failure | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Log error internally | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Show "Contact Support" message | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Allow continue to next agent | ✅ Yes | ✅ Yes | ❌ No | ❌ No
Show specific error to user | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Offer retry option | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Allow skip and add to to-do list | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Auto-retry once | ❌ No | ❌ No | ❌ No | ✅ Yes
Smart recovery suggestions | ❌ No | ❌ No | ❌ No | ✅ Yes
Escalate to specialist if persists | ❌ No | ❌ No | ❌ No | ✅ Yes
```
---
### **9. Session Resume**
```
Session Resume | Phase 0.5 | Phase 1 | Phase 2 | Phase 3
Resume from last completed agent | ✅ Yes (single user) | ✅ Yes (single user) | ✅ Yes (multi users) | ✅ Yes (multi users)
Save progress automatically | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Simple "Resume setup" button | ✅ Yes | ✅ Yes | ✅ Yes | ✅ Yes
Support multiple users | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Show progress when resuming | ❌ No | ❌ No | ✅ Yes | ✅ Yes
Graceful messaging on resume | ❌ No | ❌ No | ✅ Yes | ✅ Yes